# Smart Parking Platform

Jake Zwernemann

Information Systems Project Management

Homework 6 | Version 6.0

October 15th, 2026

## 1. Comparison of Existing Parking Apps

To begin with this project, I am going to be comparing three parking apps that I know are available in Houston which include: ParkHouston, ParkWhiz, and SpotHero. I am going to be inspecting them to see what they do, what could be improved, and what it does well. This will then help me to make a better decision about what to include for my Smart Parking Platform.

### 1.1 ParkHouston

What the App Does

The ParkHouston app is a parking app that allows users to pay for parking on their phones. It is powered by ParkMobile and the only thing users have to do is enter the zone number shown on the parking sign in front of them, choose how long they would like to park their car, and then complete their payment. The app also has a handy feature where it will send a reminder to your phone before the parking time expires. [1]

Benefits & Advantages

Drivers are able to save their unique information about their vehicles on the app for any future visits. Reminders help people keep track of their parking time before it expires. The app allows people to make reservations for selected locations. There is no need to use a parking meter. Lastly, people can add more time to their spots through the app at certain locations. [1], [2]

Problems & Limitations

Drivers might choose the wrong zone if they are not paying close enough attention when they are about to pay. [1] They also can’t exceed the time of the location’s maximum parking limit, which can become very inconvenient for those who need to stay longer than initially expected. Some locations even have another transaction fee for extending their parking time. [2]

### 1.2 ParkWhiz

What the App Does

It is an app that allows drivers to find parking by searching for an address or venue. They would then enter the date they need as well as the times. The app also shows nearby parking garages and parking lots on a map with their prices. After booking and paying, the user should receive a parking pass which will be saved on their account as well as a confirmation email. [3]

Benefits & Advantages

The map is a useful tool when comparing different parking locations that need to be close to a person’s destination. The ability to have the parking pass saved in one’s account is also super beneficial when they arrive at their parking spot. Drivers can even check vehicle height limits and see if they can leave or return during their reservation. [3]

Problems & Limitations

The app will sometimes allow people to extend their time at certain locations, but sometimes it won’t. Being able to extend one’s time is also dependent on whether there is any availability. Once a driver has already booked a time, they cannot change that arrival time afterwards. Lastly, drivers do have the ability to cancel their booked time if the reservation hasn’t already started however, the price may change for that location if they wish to book the same spot again. [3]

### 1.3 SpotHero

What the App Does

SpotHero is an app that allows drivers to find and reserve parking by entering certain information which includes parking times, their destination, and prices. They can also pay for reservations. After paying, users will receive a parking pass with proper instructions for entering their parking location. [4]

Benefits & Advantages

The app makes it incredibly easy to compare the price of certain parking locations, which allows the user to get the best deal. Being able to book ahead can allow drivers to plan their trips more efficiently and most reservations can even be cancelled for a full refund (some exceptions do apply though). [4]

Problems & Limitations

SpotHero works with certain parking locations to track availability but does not actually hold a specific parking spot open. They do offer money back however; this can cause drivers to get frustrated if they show up to their parking location and have no spot available. In addition, most locations don’t allow drivers to leave and return to their spot during the same reservation which can be difficult for those making multiple trips. [4]

### 1.4 Ideas for Parking Platform

My Smart Parking Platform will help drivers find and pay for parking by allowing them to search for parking, making reservations, comparing prices, and having an easy pay system. They will also be able to get a map-view of the locations and will see how many spots are available.

The app will also allow drivers to extend their time if needed, have proper directions to the locations, and let them easily save their parking passes to their account. Reminders will be sent out before their time expires which will prevent unnecessary confusion. The actual parking lot owners will be able to change the prices, view reservations, and update the number of open spots.

## 2. Vision and Scope

### 2.1 The Company and Project Background

$oftware ¢orp is a company that focuses primarily on creating computer systems for businesses and specifically focuses on software. The company had been asked to create a Smart Parking Platform for drivers and parking lot owners so that the drivers won’t have any more trouble finding a spot. The project was also started not only because of the availability of parking, but also to compare prices and to allow paying for a spot to be easy.  All of these ideas will be combined in an effective manner on an app as well as a website.

### 2.2 Why the Project is Needed

Drivers may experience difficulties when trying to find a parking space that is open which can cause them to waste time driving around. Parking lot owners can also have trouble updating the proper open spaces, keeping track of reservations, and making sure payments are correct. Drivers also don’t know how much these parking lots cost until they are physically there, which can cause people to become annoyed. The Smart Parking Platform app will combine all of this information into one place and make the process way smoother for everyone involved.

### 2.3 Project Scope

The app is going to include an app as well as a website which will let drivers create an account, compare pricing, search for parking availability, reserve spots, and pay easily online. The parking passes will be automatically saved to their account, drivers will receive proper directions, there will be a map to view locations, and reminders will be put in place. Extension of parking times will be included if the location allows it.

Parking lot owners will also benefit by being able to change prices, add their locations to the app, update open spots, and view payments and reservations that were made.

## 3. Software Requirements Specification

### 3.1 Purpose of the SRS

The purpose of the SRS is to be able to demonstrate what the Smart Parking Platform should be able to do. It should also include things like the big features of the app, how the system should look, and the people who are actually going to be utilizing the app.

### 3.2 Users and Technology Needed

The main users of the app are going to be parking lot owners as well as drivers. Parking lot owners will be managing their prices, parking spaces, reservations, and just generally managing their locations. Drivers will be reserving, searching, and paying for their parking. This will all be accessible through the app and website.

### 3.3 Expectations and Limitations

People using the app will need to enter the correct vehicle information as well as the correct payment. They will also need a source of internet to access the app. Parking lot owners will be held responsible for keeping their prices up to date as well as the open spaces. Only participating parking locations will be shown, and users will have to follow their parking rules.

### 3.4 Requirements for the System

The drivers will be able to save their vehicle information, create accounts, search for parking, make reservations, compare pricing, and make payments. They will also be able to receive parking passes, view maps of locations, receive reminders, and check their parking history along with their receipts. Things such as refunds, cancellations, and extra parking time will follow a certain location’s rules.

Parking lot owners will be able to manage their pricing, locations, open spots, reports, and reservations. The Smart Parking Platform system will check the proper availability to prevent any duplicate charges and limit the users to their own account details.

The app and website will protect people’s private information, and it should be easy to use. Pages should be able to load within three seconds with a good internet connection.

### 3.5 Use Cases

1. Creating an Account
Person in this scenario: Driver
Precondition: The driver does not have an account as of yet. 
Steps: The driver enters their name, email, and password and then will create the account.
Postcondition: A new account will be created.

2. Logging In the App
Person in this scenario: Driver or parking lot owner
Precondition: The user already has an account that they previously made. 
Steps: The user enters their email and password.
Postcondition: The user should be logged into the platform.

3. Adding a Vehicle
Person in this scenario: Driver
Precondition: The driver is logged into the app. 
Steps: The driver would enter their vehicle information as well as their license plate number.
Postcondition: The vehicle is saved to the corresponding account for future use.

4. Comparing Parking Choices
Person in this scenario: Driver
Precondition: Parking results are available on the app. 
Steps: The driver compares prices and the current available spaces.
Postcondition: The driver chooses the best location that suits their needs.

5. Searching for Parking
Person in this scenario: Driver
Precondition: The driver has opened the platform (the app). 
Steps: The driver enters their destination as well as the date and time. 
Postcondition: Nearby parking locations will be shown to the user.

6. Viewing Parking Information
Person in this scenario: Driver
Precondition: The driver has selected a location of their choice. 
Steps: The driver views the price, hours, rules, and available spaces.
Postcondition: The driver understands the location’s information and proceeds further.

7. Reserving a Parking Spot
Person in this scenario: Driver
Precondition: A parking spot is open and available.
Steps: The driver chooses a vehicle, date, and time and then reserves the spot.
Postcondition: If the spot is open, the driver will be able to continue to payment. The reservation will be confirmed after the payment is approved.

8. Paying for Parking
Person in this scenario: Driver
Precondition: The driver has selected a parking spot.
Steps: The driver enters their payment information and completes the payment. The system will check whether the payment has been approved and will prevent any duplicate charges. 
Postcondition: The payment and reservation are confirmed once the payment has been approved. If the payment fails, the driver will see an error and attempt again.

9. Saving a Parking Pass
Person in this scenario: Driver
Precondition: The reservation has been paid for.
Steps: The driver opens the parking pass and saves it to their phone or account.
Postcondition: The pass is ready to use at the location.

10. Getting Directions
Person in this scenario: Driver
Precondition: The driver has selected a parking location.
Steps: The driver opens the map and follows the directions.
Postcondition: The driver is properly directed to the parking location.

11. Receiving a Reminder
Person in this scenario: Driver
Precondition: The driver has an active reservation.
Steps: The system sends a reminder due to the fact that the parking time is almost over.
Postcondition: The driver knows how much time is left.

12. Extending Parking Time
Person in this scenario: Driver
Precondition: The driver has an active parking reservation. 
Steps: The driver chooses a new end time as well as pays any extra cost.
Postcondition: More time is added to the reservation after the required payment is approved. If payment fails or if more time is unavailable, the original end time will stay the same.

13. Cancelling a Reservation
Person in this scenario: Driver
Precondition: The reservation has not started.
Steps: The driver opens the reservation and selects the cancellation. The system checks the location’s cancellation and refund rules before asking the driver to confirm. 
Postcondition: The reservation is canceled and an approved refund is given back to them.

14. Resetting a Password
Person in this scenario: Driver or parking lot owner
Precondition: The user has a previously made account. 
Steps: The user is requesting a password reset and creates a new password with specific requirements. 
Postcondition: The password is now changed and can be used instantly.

15. Managing Prices and Reservations
Person in this scenario: Parking lot owner
Precondition: The owner has a participating location on the platform.
Steps: The owner updates prices and open spaces. In addition, the owner can view reservations that were made by users. The system will check that the location belongs to that owner before saving any changes. 
Postcondition: Drivers can see the updated information.

### 3.6 User Stories

1. Since I am a user, I want to be able to create an account and log in safely so I can manage my information.

2. As a driver, I want to be able to save my vehicle details so that booking parking is easier for me.

3. As a driver, I want to be able to search for parking and compare pricing, spaces, and rules so I can choose a location I like.

4. Since I am a driver, I want to be able to make a reservation, pay, and receive a pass as well as a receipt so that I am prepared when I arrive.

5. As a driver, I want to be able to view parking locations on a map and get the proper directions so I can find my parking space.

6. Since I am a driver, I want to get reminders as well as the option to request more time so I can manage when my parking is finished.

7. As a driver, I want to be able to cancel reservations and check any refunds so that I can handle changes to my plans.

8. Since I am a driver, I want to be able to see my past bookings, spending, and upcoming reservations so that I can track my parking use.

9. As a parking lot owner, I want to be able to manage my locations, prices, and my available spaces so that drivers can see the correct information.

10. Since I am a parking lot owner, I want to see reservations, payments, and reports for my locations so I can track my business status.

## 4. Work Breakdown Structure

The Work Breakdown Structure is going to be able to separate the Smart Parking Platform into smaller parts so that the project will be easier to organize and finish. It is also going to show how the different features as well as the systems will be integrated into the actual platform.

### 4.1 User Account System

##### 4.1.1 Driver Accounts

- 4.1.1.1 Create an Account

- 4.1.1.2 Log in

- 4.1.1.3 Reset a Password

- 4.1.1.4 Save Vehicle Information

- 4.1.1.5 Log Out

##### 4.1.2 Parking Lot Owner Accounts

- 4.1.2.1 Create an Owner Account

- 4.1.2.2 Log in

- 4.1.2.3 Manage Account Information

- 4.1.2.4 Add a Parking Location

- 4.1.2.5 Reset a Password

- 4.1.2.6 Log Out

- 4.1.2.7 Limit Access to the Owner’s Locations

### 4.2 Reservations and Searching for Parking

##### 4.2.1 Searching for Parking

- 4.2.1.1 Search by Location

- 4.2.1.2 Check Nearby Parking

- 4.2.1.3 Compare Pricing

- 4.2.1.4 Read the Location Details

##### 4.2.2 Parking Reservations

- 4.2.2.1 Pick a Date and Time

- 4.2.2.2 Choose a Parking Spot

- 4.2.2.3 Complete the Reservation

- 4.2.2.4 Cancel a Reservation

- 4.2.2.5 Extend Parking Time

- 4.2.2.6 View Past and Upcoming Reservations

- 4.2.2.7 Check Availability Before Booking

### 4.3 Parking Passes and the Payment System

##### 4.3.1 Parking Passes

- 4.3.1.1 Make a Parking Pass

- 4.3.1.2 Saving the Pass to an Account

- 4.3.1.3 Showing the Pass at a Parking Location

##### 4.3.2 Making the Payments

- 4.3.2.1 Choose a mode of Payment

- 4.3.2.2 Enter the Payment Information

- 4.3.2.3 Pay for the Reservation

- 4.3.2.4 Receive a receipt of the Payment

- 4.3.2.5 Process Allowed Refunds

- 4.3.2.6 Check Payment Status and Prevent Duplicate Charges

- 4.3.2.7 View Parking Spending

### 4.4 Parking Lot Management

##### 4.4.1 Parking Lot Location Information

- 4.4.1.1 Changing Parking Prices

- 4.4.1.2 Adding a Parking Lot Location

- 4.4.1.3 Changing the Parking Lot Rules

- 4.4.1.4 Updating Open Parking Spaces

##### 4.4.2 Dashboard of the Owner

- 4.4.2.1 Viewing Payments

- 4.4.2.2 Creating Reports

- 4.4.2.3 Seeing Reservations That Were Made

- 4.4.2.4 Verifying Parking Activity

### 4.5 Notifications and the Map System

##### 4.5.1 The Map System

- 4.5.1.1 Getting the Right Directions

- 4.5.1.2 Seeing the Location Information

- 4.5.1.3 Locating Parking Spots on the Map

##### 4.5.2 Notifications

- 4.5.2.1 Receiving a Reminder for Parking

- 4.5.2.2 Getting a Confirmation for a Reservation

- 4.5.2.3 Getting a Warning for Expiration

- 4.5.2.4 Acquiring a Notice of Cancellation

### 4.6 Final Release and System Testing

##### 4.6.1 Testing the System

- 4.6.1.1 Testing the Website

- 4.6.1.2 Testing the Payment System

- 4.6.1.3 Examining the Mobile App

- 4.6.1.4 Checking the Reservation System

##### 4.6.2 The Final Release

- 4.6.2.1 Fixing Any Problems

- 4.6.2.2 Performing the Final Review

- 4.6.2.3 Making the Platform Available

## 5. The Project Timeline

The Project Timeline should show when each part of the Smart Parking Platform should be worked on and completed as well. Some of these parts will have to be done before we can move onto other parts of the project. This timeline will aid in keeping the project very organized and it should help with keeping it on a proper schedule.

### 5.1 Milestones and the Timeline

| Part of the Project | Time | What Comes First | Milestone |
| --- | --- | --- | --- |
| Plan the project | Weeks 1–2 | Nothing | Requirements, roles, and budget are ready |
| Design the screens and system | Weeks 3–4 | Project plan | Designs are ready |
| Build accounts and basic owner backend | Weeks 5–6 | System design | Sprint 1 account and parking information tasks pass their checks |
| Build driver accounts and reservations | Weeks 7–8 | Basic account and parking systems | Drivers can search and create bookings waiting for payment |
| Add payments, passes, maps, and reminders | Weeks 9–10 | Reservation system | Drivers can pay, receive passes, and manage parking time |
| Build owner screens and reports | Weeks 11–12 | Basic owner backend and booking information | Owners can manage locations; drivers and owners can view reports |
| Test the full platform and fix problems | Weeks 13–14 | Main features | Main features work together and major problems are fixed |
| Complete final checks and launch | Weeks 15–16 | Testing and fixes | App and website are ready for release |

Sprint 1 is planned for weeks 5 through 6, which comes after planning and design. It will cover owner accounts and the backend for locations, open spots, and pricing. The owner screens will be added in weeks 11 & 12. Each feature will be verified as it is being created, which will be followed by full system testing in weeks 13 & 14.

### 5.2 Gantt Chart

| Task | Weeks 1-2 | Weeks 3-4 | Weeks 5-6 | Weeks 7-8 | Weeks 9-10 | Weeks 11-12 | Weeks 13-14 | Weeks 15-16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Plan the project |  |  |  |  |  |  |  |  |
| Design the screens and system |  |  |  |  |  |  |  |  |
| Build accounts and the basic owner backend – Sprint 1 |  |  |  |  |  |  |  |  |
| Build driver accounts and reservations |  |  |  |  |  |  |  |  |
| Add maps, passes, payments, and reminders |  |  |  |  |  |  |  |  |
| Build owner screens and reports |  |  |  |  |  |  |  |  |
| Test the full platform and fix problems |  |  |  |  |  |  |  |  |
| Complete final checks and launch |  |  |  |  |  |  |  |  |

Figure 1. Smart Parking Platform Gantt Chart

## 6. Product Backlog

The product backlog is a bunch of tasks that are listed out which are needed to build the Smart Parking Platform. It will include things like reports, screens for parking lot owners and the drivers, login features, and things such as processes that run behind the scenes. These tasks will help with what should be done first as well as organize the work in general.

### 6.1 Login

1. Creating a Parking Lot Owner Account: Parking lot owners should be allowed to make their own parking accounts as well as manage them for their parking locations.

2. Creating a Driver Account: Drivers should be allowed to make their own parking accounts using information such as their email, name, and password.

3. Resetting a Password: Users should be allowed to reset their password if they forget it.

4. Logging In: Drivers and parking lot owners should be allowed to access their accounts with their email and password.

5. Logging Out: Users will be allowed to sign out of their accounts safely.

### 6.2 Drivers and Parking Lot Owners User Interface

This user interface will include things like buttons and screens that people will be able to use in the app. This will aid with letting parking lot owners help manage their locations as well as help drivers find parking.

1. Parking Results Screen: This screen should show parking locations that are nearby with their available spaces and prices.

2. Parking Search Screen: This will allow drivers to be able to enter their parking times, date, and destination into the platform.

3. Reservation Screen: This will allow users to review their parking times before booking and choose their vehicle.

4. Account Screen: This will allow users to update their saved vehicle information and their contact information.

5. Dashboard of the Owner: This will give parking lot owners a summary of their parking activity and their locations.

6. Price Management Screen: This will allow parking lot owners to be able to enter and change their parking prices.

7. Map Screen: This will show the proper parking locations on a map with a button for directions.

8. Parking Pass Screen: This will show the users’ parking pass as well as instructions for entering the location they chose.

9. Managing Reservations Screen: This will let users see their reservations, request more parking time, or be able to cancel them.

10. Reports Screen: This will let users be able to see their reports about their parking activity as well as owners to see reports about their locations.

11. Parking Spaces Screen: This will let parking lot owners update the number of open parking spots.

12. Location Management Screen: This will let owners add a location or change their hours, rules, and address.

13. Owner Reservation Screen: This will let owners see reservations that were made for their location.

14. Payment Screen: This will let drivers enter their payment information as well as show the total cost.

15. Parking Details Screen: This will show the parking location’s rules, prices, hours, and address.

### 6.3 Backend Tasks

These backend tasks will handle all of the information and actions that are required to have the app work. Furthermore, it will help the system with things like managing reservations, parking locations, and payments.

1. Updating Available Spaces: It will save the number of open spaces at each parking location.

2. Finding Parking Locations: It will find parking that matches the drivers’ times, dates, and location.

3. Checking Parking Availability: It will check if a space is available for the time that was requested.

4. Process Payments: It should check whether payment has been approved, prevent any duplicate charges, and save its status. It should show an error if payment fails.

5. Creating Reservations: It will save bookings while the user’s payment is pending and it should be able to prevent more spaces from being booked than are actually available.

6. Creating Parking Passes: It will be able to create and save a parking pass after a payment is made.

7. Processing Cancellations: It should be able to free up spaces, return payments (when proper to do so), and cancel reservations.

8. Extending Parking Time: It will check the location’s rules and open spaces before adding time. Update the reservation after any required payment is approved.

9. Sending Parking Reminders: It will remind drivers of their parking time before it expires.

10. Saving Vehicle Information: It will be able to save vehicle information under the correct account.

11. Finding Owner Reservations: It should be able to find the reservations for an owner’s parking location.

12. Saving Parking Prices: It will save the prices that are entered by parking lot owners.

13. Updating Location Details: It will save changes to the location’s hours, rules, and address.

14. Controlling Account Access: It will make sure that users can only access the tools and information meant for their accounts.

15. Saving Parking Locations: It will save new parking locations under the correct account.

### 6.4 Reports

Reports will help drivers review their parking activity and help parking lot owners keep track of their parking locations.

1. Parking History Report: This report will show drivers’ reservations that happened in the past, past prices, dates, and even locations.

2. Upcoming Reservations Report: This will show users any future reservations or parking times.

3. Cancellation and Refund Report: This will show users any bookings that have been cancelled and if their money was returned.

4. Parking Spending Report: This will include showing users how much they spent on parking during a select time period.

5. Available Spots Report: This will show owners the number of open spaces at each location.

6. Busy Times of the Day Report: This will show owners which of the days and hours are the busiest with bookings.

7. Status of Payments Report: This will show what payments went through, are waiting, or flat out failed.

8. Total Reservations Report: This will include how many reservations were completed, canceled, or made.

9. Parking Revenue Report: Shows owners the money that they receive from parking payments as well as the amount refunded.

10. Receipt of Payment Report: This will give drivers a receipt for what they paid for each booking.

## 7. Sprint 1 Plan

This sprint will focus on the main topic of setting up the basic system for managing different parking lot locations. It will also aid in setting up parking lot owner accounts. These tasks should be done first due to the fact that the app needs this information before drivers can make any bookings.

### 7.1 Sprint Length and the Ultimate Goal

Sprint 1 will last two weeks, and it is planned for weeks 5 & 6. It will be focusing on owner accounts, logging in and out, and the backend for things like saving prices, locations, and open spots. Owners will only be allowed to access their own location’s information.

The backend is going to be checked before the owner screens are added in weeks 11 & 12. These tasks will only be marked complete after they pass their checks.

### 7.2 Tasks for Sprint 1

1. Updating Open Spots: This should save the number of open spots at each location.

2. Updating the Location Information: A location’s hours, address, and rules should be able to be saved.

3. Saving Locations: You should be able to save new parking locations under the right account.

4. Controlling Account Access: Make sure that owners can only manage their own locations.

5. Log In: Before allowing entry, the users’ email and password should be checked.

6. Log Out: Users should be able to safely log out of accounts.

7. Creating a Parking Lot Owner Account: Owners should be allowed to create an account to manage and update their locations.

8. Saving Prices for Parking: Parking lot owners should be able to save their prices.

### 7.3 Work Verification

Each Sprint 1 task must pass the checks listed below before being marked as complete:

- Owners can create an account, log in with their information, and log out.

- Prices and spaces cannot be negative.

- Details of locations, prices, and open spaces need to be saved correctly.

- Owners can only get into and change their own locations.

- Incorrect login information is rejected.

These checks are going to be done on the backend before the owner screens are ready. Timmy is in charge of recording any problems and testing the fixes. Josh is in charge of reviewing the results before approving completed tasks.

### 7.4 Trello Board

Figure 2. Trello Board and Sprint 1 Plan for the Smart Parking Platform

The Trello board now includes checks for all eight of the Sprint 1 tasks. Sprint 1 still remains planned for weeks 5 & 6.

Trello Board Link: https://trello.com/b/qYAbgxRa

## 8. Project Risks

This section will include possible problems that could have an effect on the Smart Parking Platform. This includes risks like tasks taking longer than initially planned, app features that aren’t working, costs that are becoming too high, and team members that are not available. These risks are grouped in financial, people, schedule, and technical risks. To be able to lower the chance of these problems happening, planning ahead would help decide what needs to be done if something does actually happen.

### 8.1 Technical Risks

Technical risks include issues with the technology that could unfortunately not make the app work as intended.

1. Incorrect Parking Availability: After making a reservation or cancellation, the app may not update the number of open spots. This could allow a driver to book a spot when there is no available spots left.

2. Issues with Accessing an Account: There could be an error that occurs where an owner can be allowed to change or view another owner’s parking information. This could make locations have the wrong prices or details.

3. Errors with Payment: If there is a connection problem, it could interrupt a payment or cause the app to show the wrong status of the payment. A driver could possibly get charged twice because of this.

4. App Crashes: The app could freeze or close when many people are using it at the same time. This could cause drivers not to be able to finish a reservation or open their parking passes when they arrive at a location.

### 8.2 Schedule Risks

Schedule risks are issues that could cause the project to miss certain deadlines or delay tasks.

1. Tasks May Take Longer Than Expected: Features that include things like making a payment or reservation may take more time to create than expected. Tasks that are not completed could be carried over into the next sprint.

2. Backend Work is Delayed: The system for saving open spots, prices, and parking locations might not be ready on time. This could cause a delay in connecting and testing the screens that use this information.

3. Testing May Find Major Problems: Testing could reveal issues that might take a longer time to fix, like reservations not saving the right way. Having to fix these issues could delay the release of the app.

4. Extra Features are Requested: There might be new features that are wanted after the schedule is set. Adding extra features could make it so there is less time to finish the original features that were planned.

### 8.3 Financial Risks

Financial risks are issues that could make the project cost more than originally planned or make it so there is not enough money to complete it.

1. App Running Costs Go Up: Having to store the app’s information and keeping it online might cost more than expected as more people continue to use it. This could make monthly costs go up.

2. Unexpected Software Costs: Paid plans might be required for some features such as things like the map. These costs could use money meant for other project tasks.

3. More Development Costs: Having to fix major issues or remaking features could require more work hours that are paid than originally planned. This could make the project go over its budget.

4. Funding Goes Down: There might be less money that was received for the project than expected. Some features might be delayed or the amount of work done needs to be reduced for the first release.

### 8.4 People Risks

People risks are when there are issues involving team members that could have an effect on how work is completed.

1. Lack of Experience: Some members may not know how to create certain features, such as account security or things like payments. They may need extra help or training before they can achieve these tasks.

2. Poor Communication: Some members could miss updates about changes to the app. This could make them repeat work that someone else already did or build features with old information.

3. Workload is Uneven: One person could receive too many tasks while another has too little. That could make a person fall behind or make mistakes while rushing to get everything done on time.

4. A Member Becomes Unavailable: An illness or other things could cause a member to leave the project or miss work. Someone would have to take over their tasks, and it could delay the project’s progress.

## 9. Risk Register

The risk register will list possible problems as well as how likely they are to happen. Also, it will include how much they affect the project, who will track each risk, what action will be taken, and its current status. Things like impact and probability are rated as low, medium, or high.

| Risk ID | Risk Description | Probability | Impact | Person Responsible | Response Strategy | Status / Notes |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | Incorrect Parking Availability | Medium | High | Backend Developer (Olivia Hayes) | Mitigate: Update space counts & check availability before booking. | Open — response is planned; testing has not started. |
| R02 | Payment Errors | Medium | High | Backend Developer (Olivia Hayes) | Mitigate: Check payment status and block any duplicate charges. | Open |
| R03 | Account Access Problems | Medium | High | Backend Developer (Olivia Hayes) | Mitigate: Check so that owners can only access their locations. | Open |
| R04 | Tasks Take Longer Than Expected | High | Medium | Project Manager (Josh Smith) | Mitigate: Break tasks into smaller steps and go over progress weekly. | Open |
| R05 | Backend Work is Delayed | Medium | High | Backend Developer (Olivia Hayes) | Mitigate: Finish basic backend work in Sprint 1 and report delays early. | Open |
| R06 | Extra Features Are Requested | Medium | Medium | Project Manager (Josh Smith) | Mitigate: Review new requests and move optional features to later sprints. | Open |
| R07 | Higher App Running Costs | Medium | Medium | Project Manager (Josh Smith) | Mitigate: Track monthly costs and introduce spending alerts. | Open |
| R08 | Less Funding Available | Low | High | Project Manager (Josh Smith) | Mitigate: Confirm funding and make essential features first. | Open |
| R09 | Team Member Becomes Unavailable | Medium | High | Project Manager (Josh Smith) | Mitigate: Keep shared task notes and assign backup team members. | Open |
| R10 | Poor Communication | Medium | Medium | Project Manager (Josh Smith) | Mitigate: Have regular updates and document new things in Trello. | Open |

Table 1. Risk Register for the Smart Parking Platform

## 10. Communication Plan

This plan will explain how progress will be shared, how problems will be reported, and when the members will meet.

### 10.1 Team Meetings

- Testing Team: Will meet twice a week during testing to check fixes, verify any errors, and decide what they need to test next.

- Stakeholders: They will meet at the end of every two-week sprint to see the finished work, give feedback, and discuss about any delays.

- The Complete Project Team: Will meet once a week to review things like deadlines, costs, risks, and progress. The project manager will make sure to assign more follow up tasks and record the decisions.

- The Development Team: They will meet for 10-15 minutes every single workday to talk about upcoming work, problems that need to be fixed, and completed work.

### 10.2 Sharing Updates

- Meeting Notes: The leader of the meeting will assign tasks, save any decisions made, and save deadlines in a shared document after each of the meetings.

- Trello: Members will be updating their cards as work progresses. Timmy will be recording test results, and Josh will be approving tasks before they move to the Done column. Any delays will be reported to Josh.

- Emailing Updates: The project manager will send the stakeholders an update after each of the sprints. It will make sure to cover unfinished work, finished work, major risks, and any plans for the next sprint.

- Urgent Issues: Members will get in touch with the project manager through the team chat when a serious issue is found. The project manager will notify the people who were affected and record any next steps.

## 11. Resources and Roles

This section will explain who will be working on the Smart Parking Platform and what each person will be doing. It will include things like their skill levels, their names, and the percentage of their work time that has been assigned to the project at hand. These will include made-up names for this project, and the time commitments as well as the skill levels will just be estimates.

### 11.1 Project Team

| Role | Made Up Name | Main Tasks | Skill Level | Time Assigned |
| --- | --- | --- | --- | --- |
| Project Manager | Josh Smith | Tracks costs and deadlines, shares updates, and approves completed tasks. | Experienced | 25% |
| Screen Designer | Liam Carter | Designs the screens and makes buttons and menus easy to use. | Intermediate | 25% |
| Frontend Developer | Brody Reed | Builds the screens that drivers and owners use and connects them to the backend. | Intermediate | 75% |
| Backend Developer | Olivia Hayes | Builds the backend, starting with owner accounts and parking information in Sprint 1. | Experienced | 75% |
| Tester | Timmy Turner | Tests features during each sprint, records problems, and checks fixes. | Intermediate | 50% |

A team member that is experienced can handle more difficult tasks with almost no help, while an intermediate member can complete regular tasks but might need extra help with harder work.

The percentages in the table above are the average time commitments for the entire 16-week project. So, based on a 40-hour workweek, 25% would mean 10 hours per week, 50% would mean 20 hours a week, and 75% would mean 30 hours a week.

## 12. Cost and Resource Plan

This plan will be estimating the costs of making the Smart Parking Platform over the entire 16 weeks. The team costs will be determined by multiplying each person’s work hours that have been planned by an hourly rate. For other costs like software tools and hosting, they will be added with extra money just in case any unexpected issue occurs. This plan will be utilizing bottom up estimating.

### 12.1 Team Costs

For the table below, each person’s total hours are being based on their average weekly hours which have been multiplied by 16 weeks.

| Role | Total Hours | Hourly Rate | Total Cost |
| --- | --- | --- | --- |
| Screen Designer | 160 | $35 | $5,600 |
| Project Manager | 160 | $45 | $7,200 |
| Frontend Developer | 480 | $40 | $19,200 |
| Backend Developer | 480 | $45 | $21,600 |
| Tester | 320 | $30 | $9,600 |
| Total | 1,600 |  | $63,200 |

### 12.2 Other Project Costs

The project is also going to require things such as outside services, software tools, and more. I have divided the 16-week project into four planning months which include 4 weeks each.

| Item | Purpose | Cost Calculation | Total |
| --- | --- | --- | --- |
| Hosting Storage & Data Storage | Keeps the platform online and will store its information. | $180 × 4 months | $720 |
| Software Tools | Provides tools for designing as well as building and testing the app. | $85 × 4 months | $340 |
| Map and Reminder Services | Supports parking maps and driver reminders. | $60 × 4 months | $240 |
| Test Devices | Provides phones for testing the app. | $250 × 2 phones | $500 |
| Total Other Costs |  |  | $1,800 |

The team will be using the computers that it already has so there isn’t an unnecessary cost for that. Testing the payment portion of the platform will be using a test system without any real charges going through. After launching the platform, payment processing fees will be outside of the development budget.

### 12.3 Total Project Budget

There will be an extra 10% of the budget that will be set aside to account for any unexpected costs. These include things such as higher service costs or the need for any additional testing. This extra money will only be used if truly required.

| Budget Item | Amount |
| --- | --- |
| Team Costs | $63,200 |
| Other Project Costs | $1,800 |
| Subtotal | $65,000 |
| Extra Money for Unexpected Costs (10%) | $6,500 |
| Total Planned Budget | $71,500 |

### 12.4 Budget Plan (Monthly)

The table below will be depicting how the budget will be divided across our four planning months. This will include four weeks in each month. The team costs will be spread evenly for this, and both test phones are going to be purchased in the first month.

| Month | Team Costs | Other Costs | Extra Money Set Aside (10%) | Total Budget |
| --- | --- | --- | --- | --- |
| Month 1: Weeks 1–4 | $15,800 | $825 | $1,662.50 | $18,287.50 |
| Month 2: Weeks 5–8 | $15,800 | $325 | $1,612.50 | $17,737.50 |
| Month 3: Weeks 9–12 | $15,800 | $325 | $1,612.50 | $17,737.50 |
| Month 4: Weeks 13–16 | $15,800 | $325 | $1,612.50 | $17,737.50 |
| Total | $63,200 | $1,800 | $6,500 | $71,500 |

The monthly costs that are going to be regular for this project include $180 for hosting, $60 for the map and reminder services, and $85 for any software tools. Month 1 is higher because we are spending $500 on the two test phones. All of the extra money will only be spent if truly needed.

## 13. RACI Matrix

This table depicts each team member’s responsibility for the project tasks at hand.

- R – Responsible: Completes their respective task.

- A – Accountable: Makes sure the task is completed and then approves it.

- C – Consulted: Member gives feedback or advice.

- I – Informed: Member receives any updates.

Each task on the table will have one person that is marked with an A. If a person is marked with both A & R, then that means that person completes and approves that particular task.

| Task | Josh — Project Manager | Liam — Screen Designer | Brody — Frontend Developer | Olivia — Backend Developer | Timmy — Tester |
| --- | --- | --- | --- | --- | --- |
| Plan the schedule as well as the budget | A/R | C | C | C | C |
| Decide what the app needs to do | A/R | C | C | C | C |
| Design the app screens | A | R | C | C | C |
| Build the app screens | A | C | R | C | C |
| Make accounts and control access | A | I | C | R | C |
| Build the booking as well as the payment features | A | I | C | R | C |
| Connect the screens to the backend | A | C | R | R | C |
| Test the app and report any problems | A | C | C | C | R |
| Fix problems found during testing | A | C | R | R | C |
| Launch the app and website | A | I | R | R | C |
| Send updates to the stakeholders | A/R | I | I | I | I |
| Build backend for locations, prices, and spaces | A | I | C | R | C |

Sources

[1] ParkMobile, LLC. “ParkHouston.” Google Play. ParkHouston app description. Accessed September 10, 2026.

[2] ParkMobile. “Can I extend a parking session?” ParkMobile Customer Care. Parking session extension information. Accessed September 10, 2026.

[3] ParkWhiz. “How to book parking.” ParkWhiz booking instructions. Accessed September 10, 2026.

[4] SpotHero. “Find and Compare Parking in Houston.” Houston parking page. Accessed September 10, 2026.